## Week 1
Weekly report
Report Date | 14/04/2019
Report Week | 1
Report By | Dang Ho Vu
Tasks on this week
Task# | Description | Status | Note
1 | Write api to create Event | Done
2 | Get list of upcoming activities and render to it in Salerep 's dashboard. | Done
3 | Pagin, sorting, filtering upcoming activities | Done
4 | Handle actions in market plan phase | In-Progress
Tasks on next week
Task# | Description | Status | Note
1 | Finish "handle actions in market plan phase"
2 | Research Gmail API
3 | Implement Gmail API to send mail to contact
Team member comments
MemberID | Comment | Overall | Expectation
QuangVTT | He works hard, efficiently | Good
AnhTD | He works hard, efficiently and takes part in all team meeting | Good